## Read me
Action plan template
Action plan: one row per action. Fill in the yellow cells: the goal it serves, the action (start with a verb), one owner, the start and due dates, the status and the % complete.
Days left and Flag are worked out from today's date. Flag shows Overdue (red) once the due date has passed and the action isn't Done, Due soon (amber) in the last 7 days, and Late start (amber) if the start date has passed and the action still hasn't started.
Status is a drop-down: Not started, In progress, At risk (amber), Blocked (red), Done (green).
Example - Action plan: a fictional company's plan, to show the level of detail that works. Delete it once you no longer need it.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## Action plan
Action plan: [goal or plan name]
One row per action. Start each action with a verb and give it one owner.
Plan owner
Agreed on
Next review
Goal | Action | Owner | Start | Due date | Status | % complete | Days left | Flag | Resources or cost | Notes and evidence
Formulas:
Days left = IF(OR([Due date]="",[Status]="Done"),"",[Due date]-TODAY())
Flag = IF(OR([Action]="",[Due date]=""),"",IF([Status]="Done","Done",IF([Due date]<TODAY(),"Overdue",IF([Due date]-TODAY()<=7,"Due soon",IF(AND([Start]<>"",[Start]<TODAY(),OR([Status]="",[Status]="Not started")),"Late start","")))))

## Example - Action plan
Action plan: [goal or plan name]: example
Example: a fictional 55-person engineering consultancy's plan to collect cash faster. Days left and Flag use today's date, so they change as time passes.
Plan owner
Agreed on
Next review
Goal | Action | Owner | Start | Due date | Status | % complete | Days left | Flag | Resources or cost | Notes and evidence
Clients pay within 45 days on average by 31 Mar | Agree 30-day payment terms in every new contract | Commercial director | 2026-11-02 | 2026-11-30 | Done | 100% |  |  | Two hours of legal review | New contract template in use from 27 Nov
Clients pay within 45 days on average by 31 Mar | Send each invoice on the day the project milestone is signed off | Finance manager | 2026-11-09 | 2026-12-18 | In progress | 60% |  |  |  | Three of five project leads now copy sign-off emails to finance
Clients pay within 45 days on average by 31 Mar | Phone clients 7 days before each invoice is due | Credit controller | 2026-11-16 | 2027-01-29 | In progress | 30% |  |  | Four hours a week | Call script drafted
Clients pay within 45 days on average by 31 Mar | Offer card and direct debit payment on invoices under £5,000 | Finance manager | 2026-12-01 | 2027-01-15 | At risk | 20% |  |  | Card fees on small invoices | Bank set-up form returned for a missing signature
Board can see progress | Add debtor days to the monthly KPI dashboard | Finance manager | 2026-11-02 | 2026-11-27 | Blocked | 50% |  |  |  | Waiting for the accounts system supplier to build the report
Fewer invoice disputes | Put the purchase order number and project code on every invoice | Accounts assistant | 2026-11-02 | 2026-11-13 | Done | 100% |  |  |  | Invoice template changed
Fewer invoice disputes | Review last year's 10 largest disputed invoices and fix the causes | Commercial director | 2027-01-04 | 2027-02-26 | Not started | 0% |  |  | One day
Formulas:
Days left = IF(OR([Due date]="",[Status]="Done"),"",[Due date]-TODAY())
Flag = IF(OR([Action]="",[Due date]=""),"",IF([Status]="Done","Done",IF([Due date]<TODAY(),"Overdue",IF([Due date]-TODAY()<=7,"Due soon",IF(AND([Start]<>"",[Start]<TODAY(),OR([Status]="",[Status]="Not started")),"Late start","")))))