## Read me
Capacity planning template
Capacity plan: one row per team (or person, or machine) per week. Available hours = people x hours per person - leave and absence - meetings, admin and training.
Utilisation = planned demand / available hours. Spare (+) or short (-) is available hours minus planned demand.
Flag: Over capacity (red) when demand is more than the hours available, Above target (amber) when utilisation is over the team's target, OK (green) otherwise.
Example - Capacity plan: a fictional IT support company's four teams over two weeks in March.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## Capacity plan
Capacity plan: [team or department]
One row per team per week, in hours for the whole team. Set a target utilisation below 100% for each team.
Department or site
Prepared by
Last updated
Week starting | Team or resource | People (FTE) | Hours per person per week | Leave and absence (hours) | Meetings, admin and training (hours) | Available hours | Planned demand (hours) | Utilisation | Spare (+) or short (-) hours | Target utilisation | Flag | Action or note

## Example - Capacity plan
Capacity plan: [team or department]: example
Example: a fictional 52-person IT support company over two weeks in March. Replace the rows with your own teams.
Department or site
Prepared by
Last updated
Week starting | Team or resource | People (FTE) | Hours per person per week | Leave and absence (hours) | Meetings, admin and training (hours) | Available hours | Planned demand (hours) | Utilisation | Spare (+) or short (-) hours | Target utilisation | Flag | Action or note
2027-03-01 | Service desk | 12 | 37.5 | 37.5 | 30 |  | 300 |  |  | 75% |  | Over target both weeks; hold new leave requests
2027-03-01 | Projects | 8 | 37.5 | 0 | 20 |  | 312 |  |  | 85% |  | Client office move; 30 hours of cabling to field engineers
2027-03-01 | Field engineers | 10 | 37.5 | 75 | 25 |  | 210 |  |  | 80% |  | Take on cabling and site surveys for the move
2027-03-01 | Onboarding | 3 | 37.5 | 0 | 8 |  | 60 |  |  | 85%
2027-03-08 | Service desk | 12 | 37.5 | 75 | 30 |  | 290 |  |  | 75%
2027-03-08 | Projects | 8 | 37.5 | 37.5 | 20 |  | 330 |  |  | 85% |  | Second project moved to start on 15 March; overtime agreed
2027-03-08 | Field engineers | 10 | 37.5 | 37.5 | 25 |  | 240 |  |  | 80%
2027-03-08 | Onboarding | 3 | 37.5 | 0 | 8 |  | 64 |  |  | 85%