## Read me
Decision log template
Decision log: one row per significant decision, added on the day it's made. The ID numbers itself (D001, D002 and so on).
For each decision, record what was decided, the context, the options considered, why this option won, who decided, the impact and a review date.
Status is a drop-down: Proposed (amber), Agreed (green), Implemented (green), Superseded, Reversed (red). Review flag turns amber once the review date arrives.
Never overwrite an old decision. Add a new row, set the old one to Superseded and enter the new ID in its Superseded by column.
Example - Decision log: six decisions from a fictional company.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## Decision log
Decision log: [project, team or board]
One row per decision. Keep superseded decisions; don't overwrite them.
Log owner
Updated on
ID | Date | Decision | Context (why a decision was needed) | Options considered | Why this option | Decided by | Impact (cost, people, systems) | Review date | Status | Review flag | Superseded by | Where recorded
D001
D002
D003
D004
D005
D006
D007
D008
D009
D010
D011
D012
D013
D014
D015
D016
D017
D018
D019
D020
D021
D022
D023
D024
D025
D026
D027
D028
D029
D030
D031
D032
D033
D034
D035
D036
D037
D038
D039
D040
D041
D042
D043
D044
D045
D046
D047
D048
D049
D050
D051
D052
D053
D054
D055
D056
D057
D058
D059
D060
Formulas:
Review flag = IF(OR([Decision]="",[Review date]="",[Status]="Superseded",[Status]="Reversed"),"",IF([Review date]<=TODAY(),"Review due",""))

## Example - Decision log
Decision log: [project, team or board]: example
Example: decisions from a fictional 70-person building maintenance contractor. D002 shows how a superseded decision stays in the log.
Log owner
Updated on
ID | Date | Decision | Context (why a decision was needed) | Options considered | Why this option | Decided by | Impact (cost, people, systems) | Review date | Status | Review flag | Superseded by | Where recorded
D001 | 2026-08-24 | Replace our three job systems with one job-management system | Scheduling, timesheets and invoicing sit in separate systems, so the office keys every job in twice | Keep all three; link them together; replace them with one system | Linking them would cost almost as much as replacing them, and one system ends the double keying | Board | £28,000 in year one; training for 25 office staff | 2027-08-31 | Agreed |  |  | Board minutes, 24 Aug, item 5
D002 | 2026-09-07 | Go live with the new system on 4 January | Office is quieter after the Christmas break | 4 January; after the March year end | January avoids a clash with the year end | Operations director | Old system licence ends on 31 December | 2026-11-30 | Superseded |  | D005 | Project meeting, 7 Sep
D003 | 2026-09-14 | Lease eight electric vans as the diesel leases end | Six diesel van leases end in November and two more next year | Renew the diesel leases; buy used diesel vans; lease electric vans | Lower running costs over four years outweigh the higher lease cost; chargers fit at the depot | Board | £1,100 a month more in leases; £14,000 for depot chargers; driver training | 2027-06-30 | Implemented |  |  | Board minutes, 14 Sep, item 3
D004 | 2026-09-28 | Fixed prices for small jobs under £1,500 instead of site quotes | Estimators spend a day a week quoting small jobs that rarely go ahead | Keep quoting; charge for quotes; a fixed-price menu | Keeps small customers without tying up estimators | Managing director | Menu prices to be updated every six months | 2027-03-31 | Agreed |  |  | Email to the leadership team, 28 Sep
D005 | 2026-10-12 | Move go-live for the new system to 4 May, after the year end | Supplier can't move the historic job records before February, and March is the year end | Go live in January without job history; go live in March; go live in May | Engineers need job history on their phones from day one, and March would clash with the year end | Operations director | Old system licence extended to May: £3,800 | 2027-02-15 | Agreed |  |  | Project meeting, 12 Oct
D006 | 2026-10-12 | Office staff in the office Tuesday to Thursday | Teams have drifted into different patterns and new starters are learning slowly at home | Five days in the office; fully flexible; three set days | Gives new starters time alongside experienced staff and keeps two flexible days | Leadership team | Desk booking needed midweek; hybrid working policy to be updated | 2027-04-30 | Proposed |  |  | Leadership meeting, 12 Oct; staff feedback due 30 Oct
Formulas:
Review flag = IF(OR([Decision]="",[Review date]="",[Status]="Superseded",[Status]="Reversed"),"",IF([Review date]<=TODAY(),"Review due",""))