## Read me
Gantt chart template
Gantt chart: one row per task. Enter the task, owner, start date, working days and % done. The end date (counting working days, skipping weekends), the status and the bars across the 26-week timeline fill in automatically. Dark bar = done so far; light bar = still to do.
Change the timeline start (C3) to the Monday your project begins.
Example: a fictional company moving to a new accounts system, to show the layout.
Status uses today's date: Late means the end date has passed and the task isn't 100% done.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## Gantt chart
Gantt chart
One row per task. Bars draw themselves from the start date and duration.
Timeline starts (a Monday) |  | 2026-11-02
Task | Owner | Start | Days | End | % done | Status

## Example
Gantt chart: example
Example: a fictional company moving to a new accounts system.
Timeline starts (a Monday) |  | 2026-11-02
Task | Owner | Start | Days | End | % done | Status
Agree scope and budget | Finance director | 2026-11-02 | 5 |  | 100%
Shortlist and demo three systems | Finance manager | 2026-11-09 | 10 |  | 100%
Choose system and sign contract | Finance director | 2026-11-23 | 5 |  | 50%
Map current processes and reports | Finance manager | 2026-11-23 | 10 |  | 20%
Clean supplier and customer records | Accounts assistant | 2026-11-30 | 15 |  | 0%
Configure chart of accounts | Implementation partner | 2026-12-07 | 10 |  | 0%
Migrate opening balances | Finance manager | 2027-01-04 | 5 |  | 0%
Train the finance team | Implementation partner | 2027-01-11 | 5 |  | 0%
Parallel run (old and new) | Finance team | 2027-01-18 | 20 |  | 0%
Go live and switch off old system | Finance director | 2027-02-15 | 2 |  | 0%