## Read me
RACI matrix template
RACI matrix: one row per task or decision, one column per role. Pick R, A, C or I from the drop-down in each cell, and leave it blank if that role plays no part.
R = Responsible (does the work). A = Accountable (owns the result; exactly one per row). C = Consulted (asked before). I = Informed (told after).
Type your own role names over the six role headings. To add a role, insert a column between two role columns so the check counts it, and copy a role column's cells into it to bring the drop-downs.
Check says OK when a row has exactly one A, and 'Check: needs one A' when it has none or more than one.
Example - RACI matrix: a fictional 50-person company replacing its office phone system.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## RACI matrix
RACI matrix: [project or process]
One row per task or decision. Roles across the top: type your own over the headings. One A per row.
Project
Prepared by
Agreed on
Stage | Task or decision | Sponsor | Project lead | Finance | Operations | IT | Supplier | Check | Notes

## Example - RACI matrix
RACI matrix: [project or process]: example
A fictional 50-person company replacing its phone system. The switch-over row has two As on purpose, to show the check.
Project
Prepared by
Agreed on
Stage | Task or decision | Sponsor | Project lead | Finance | Operations | IT | Supplier | Check | Notes
Plan | Approve the budget | A | R | C | I | C
Plan | Choose the new phone supplier | A | R | C | C | C
Build | Design the call routing: which calls go to which team | I | C |  | A | C | R |  | Operations knows the call patterns best
Build | Move the existing numbers to the new provider |  | A |  | I | C | R
Build | Set up handsets, headsets and the mobile app |  | I |  | C | A | R
Launch | Train staff on the new system |  | A |  | C | R | R |  | Supplier trains team leaders; IT trains everyone else
Launch | Decide the switch-over date | A | A |  | C | C | C |  | Two As on purpose: the check flags it
Close | Cancel the old phone contract | I | C | A |  | R |  |  | Check the notice period first