## Read me
RAID log template
RAID log: one row per risk, assumption, issue or dependency. Choose the type from the drop-down, then add the description, likelihood and impact, the response, an owner, a due date and a status.
Likelihood and impact run from 1 to 5. For an assumption, score the chance it proves wrong; for a dependency, the chance it arrives late; for an issue, enter 5, because it has already happened.
Score is likelihood x impact. Rating: High at 15 or more, Medium from 8 to 14, Low at 7 or less.
Overdue? shows Overdue when the due date has passed and the status isn't Closed.
Example - RAID log: a fictional 85-person training company opening a second training centre.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## RAID log
RAID log: [project name]
One row per item. Filter the Type column to see one letter at a time. Close rows instead of deleting them.
Project
Manager
Reviewed
ID | Type | Description | Raised | Likelihood (1-5) | Impact (1-5) | Score | Rating | Response or next action | Owner | Due date | Status | Overdue? | Notes
01
02
03
04
05
06
07
08
09
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
Formulas:
Overdue? = IF(OR([Due date]="",[Status]="Closed"),"",IF([Due date]<TODAY(),"Overdue",""))

## Example - RAID log
RAID log: [project name]: example
Example rows for a fictional company. Replace them with yours.
Project
Manager
Reviewed
ID | Type | Description | Raised | Likelihood (1-5) | Impact (1-5) | Score | Rating | Response or next action | Owner | Due date | Status | Overdue? | Notes
01 | Risk | Fit-out contractor finishes late, so the March courses can't run in the new centre | 2026-11-09 | 3 | 4 |  |  | Weekly site meeting; training rooms finished first; March courses can move to the existing centre if needed | Operations manager | 2027-01-29 | Open
02 | Assumption | Two experienced trainers will transfer from the existing centre | 2026-11-09 | 2 | 4 |  |  | Confirm with each trainer in writing; line up a freelance trainer as cover | Managing director | 2026-12-11 | Open
03 | Dependency | Booking system supplier adds the new venue to the online booking pages | 2026-11-09 | 3 | 3 |  |  | Change ordered; supplier to confirm a release date | Sales manager | 2027-01-15 | Open
04 | Risk | Broadband line not installed in time for opening | 2026-11-09 | 3 | 4 |  |  | Order placed early; chase the provider every fortnight | IT lead | 2026-11-23 | Closed |  | Happened on 23 Nov: see 05
05 | Issue | Broadband installation put back three weeks, to 22 February | 2026-11-23 | 5 | 4 |  |  | 4G router as a stop-gap; escalated to the provider's account manager | IT lead | 2026-12-04 | Escalated |  | Came from risk 04
06 | Risk | Bookings for the first three months fall short of plan | 2026-11-09 | 3 | 5 |  |  | Early-booking offer to existing clients in the region from January | Sales director | 2027-01-08 | Open
07 | Assumption | The landlord will approve a sign on the front of the building | 2026-11-09 | 2 | 2 |  |  | Ask for written consent before ordering the sign | Office manager | 2026-11-27 | Closed |  | Consent received 20 Nov
08 | Dependency | Furniture delivered before the trainers' set-up week | 2026-11-16 | 2 | 3 |  |  | Delivery booked for 15 February; supplier to confirm a week before | Office manager | 2027-02-08 | Open
Formulas:
Overdue? = IF(OR([Due date]="",[Status]="Closed"),"",IF([Due date]<TODAY(),"Overdue",""))