## Read me
Risk register template
Register: one row per risk, with formulas for 100 risks. Score likelihood and impact from 1 to 5; the score (1-25) and rating calculate automatically: 15 or more is High, 8-14 Medium, 7 or less Low.
Residual likelihood and impact are the scores once your controls are in place. Base decisions on these.
Heat map: counts the risks in the Register by likelihood and impact.
Scoring guide: the scales. Adjust the impact descriptions to your company's size once, then keep them fixed.
Example risks: ten risks for a fictional mid-sized company that you can copy into the Register.
Pale yellow cells are inputs. Everything else is calculated.
Free template from runbooked.co

## Register
Risk register
One row per risk. Score likelihood and impact from 1 to 5 using the Scoring guide sheet.
ID | Risk (what could happen) | Category | Cause | Consequence | Owner | Likelihood (1-5) | Impact (1-5) | Score | Rating | Existing controls | Further action | Action owner | Due date | Status | Residual likelihood | Residual impact | Residual score | Residual rating | Last reviewed
R01
R02
R03
R04
R05
R06
R07
R08
R09
R10
R11
R12
R13
R14
R15
R16
R17
R18
R19
R20
R21
R22
R23
R24
R25
R26
R27
R28
R29
R30
R31
R32
R33
R34
R35
R36
R37
R38
R39
R40
R41
R42
R43
R44
R45
R46
R47
R48
R49
R50
R51
R52
R53
R54
R55
R56
R57
R58
R59
R60
R61
R62
R63
R64
R65
R66
R67
R68
R69
R70
R71
R72
R73
R74
R75
R76
R77
R78
R79
R80
R81
R82
R83
R84
R85
R86
R87
R88
R89
R90
R91
R92
R93
R94
R95
R96
R97
R98
R99
R100

## Heat map
Heat map
Number of risks in the Register at each likelihood and impact (before controls).
Impact
5
4
3
2
1
| 1 | 2 | 3 | 4 | 5
Likelihood

## Scoring guide
Scoring guide
Adjust the descriptions to your company once, then keep them fixed.
Score | Likelihood | Rough chance in the next 12 months
1 | Rare | Under 5%
2 | Unlikely | 5-20%
3 | Possible | 20-50%
4 | Likely | 50-80%
5 | Almost certain | Over 80%
Score | Impact | What it would mean (example; set your own)
1 | Negligible | Small cost absorbed in the month; no customer notices
2 | Minor | Noticeable cost or delay; a few customers affected
3 | Moderate | Hits the quarter's profit; some customers affected; management time for weeks
4 | Major | Wipes out a large part of the year's profit; key customers or staff lost; regulator interest
5 | Severe | Threatens the company's survival
Score (likelihood x impact) | Rating
15-25 | High
8-14 | Medium
1-7 | Low

## Example risks
Risk register: example risks
Example risks for a fictional mid-sized company. Copy or adapt them.
ID | Risk (what could happen) | Category | Cause | Consequence | Owner | Likelihood (1-5) | Impact (1-5) | Score | Rating | Existing controls | Further action | Action owner | Due date | Status | Residual likelihood | Residual impact | Residual score | Residual rating | Last reviewed
R01 | Our largest customer moves to a competitor | Commercial | Contract renewal with no relationship plan | Revenue falls and costs must be cut | Sales director | 3 | 4 |  |  | Quarterly account reviews; renewals tracked six months ahead | Agree a key-account plan for the top five customers | Sales director |  | Open
R02 | Ransomware locks the file server after a phishing email | Cyber | A member of staff opens a malicious attachment | Can't work or invoice for days; possible data breach | IT manager | 3 | 5 |  |  | Email filtering; daily backups | Keep an offline backup; run phishing training | IT manager |  | Open
R03 | Only one person can run payroll and month-end | People | Knowledge kept in one person's head | Payroll late or wrong if they're away or leave | Finance director | 3 | 4 |  |  | Partial notes | Write SOPs and train a deputy | Finance director |  | Open
R04 | Cash runs short in a quarter with VAT and tax due | Financial | Customers pay late while tax bills fall due | Can't pay suppliers or salaries on time | Finance director | 3 | 4 |  |  | 13-week cash flow forecast; credit control process | Agree an overdraft facility before it's needed | Finance director |  | Open
R05 | A fake email changes a supplier's bank details | Fraud | Invoice redirection scam | Payment lost to fraudsters | Finance manager | 3 | 3 |  |  | Call-back check on any bank detail change | Add the check to the payments SOP | Finance manager |  | Open
R06 | Our sole supplier of a key component fails | Operational | Supplier in financial difficulty | Production stops for weeks | Operations manager | 2 | 4 |  |  | Annual supplier credit check | Qualify a second supplier | Operations manager |  | Open
R07 | Customer personal data is emailed to the wrong person | Compliance | Email autocomplete | Reportable data breach; loss of trust | Data protection lead | 3 | 3 |  |  | Data protection training | Add a delay on outgoing email | Data protection lead |  | Open
R08 | An employee is injured lifting stock | Health and safety | Heavy items stored at height | Injury, absence and a possible claim | Operations manager | 2 | 4 |  |  | Manual handling training; risk assessments | Move heavy stock to low racking | Operations manager |  | Open
R09 | The accounts system is down for several days | Operational | Provider outage | Invoicing and payments delayed | IT manager | 2 | 3 |  |  | Cloud provider's service level; weekly exports | Document a manual invoicing fallback | IT manager |  | Open
R10 | A fire or flood makes the office unusable | Premises | Fire, flood or loss of access | Staff can't work from the office | Managing director | 1 | 5 |  |  | Insurance; laptops; business continuity plan | Test working from home once a year | Managing director |  | Open